## Project Plan
Final Project
Project Lead: Team 1
Features and Description | Estimated Implementation | Assigned To | Status
Not Implemented
In Progress
Done
Set up Unity and Github projects | 2019-11-06 | Lauren | Done
Find environment and theme assets | 2019-11-06 | Lucas | Done
Find mobs and boss models with animations | 2019-11-06 | Andrew | Done
Find Player model, add all animations | 2019-11-06 | Lauren | Done
Create main menu/canvas scene, connect all functionality, make buttons | 2019-11-13 | Lauren | Not Implemented
Mock up level design | 2019-11-13 | Lucas | Done
Program Character Controller (Movement) | 2019-11-13 | Andrew | Done
Program TriggerEvents for doors, implement level design | 2019-11-20 | Lucas | Not Implemented
Program Shoot and Slash functions | 2019-11-20 | Andrew | In Progress
Program Enemy AI states | 2019-11-20 | Andrew | Done
Program Pickup System | 2019-11-25 | Lucas | In Progress
Develop Scoring System (Completion? Timer?) | 2019-11-25 | Lauren | Not Implemented
Design overheat mechanic for limiting shooting | 2019-11-25 | Lauren | Not Implemented
Design health UI for player plus script | 2019-11-25 | Lauren | Not Implemented
Add vignette to camera, camera transitions for rooms | 2019-12-06 | Lauren | Not Implemented
Add stealth ability? | 2019-12-06 | Lucas | Not Implemented
Add in BGM and sound effects | 2019-12-06 | Group effort | Not Implemented
Insert a row above to add more features to the list.